­

Progress Report
Community Plan 2022-2032
Quarter 4 2024-25 (April to March)

Summary - number of actions complete, green, amber, red and to be reported later under each Priority

Priority areas of action	Complete	Green	Status Amber	Red	To be reported later	Total
Putting learning at the centre	0	11	0	0	0	11
Our children and young people thrive	2	14	0	0	0	16
Thriving businesses and fair jobs	0	10	0	2	0	12
Caring, connected communities	2	13	0	0	0	15
Good quality, suitable housing for everyone	1	11	1	1	0	14
People live the healthiest lives possible	0	7	1	0	0	8
Total	5	66	2	3	0	76

       Key:

Statistical Measures
Project Measures

Putting learning at the centre / We will work with and support people of all ages to help them re-engage with education and learning or to improve their employability skills

Outcome: People experiencing barriers to employment are supported into sustainable work

				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
A.1.1	Provide key worker based employability support and learning to targeted groups	Increase the percentage of employability participants progressing to positive destinations	Currently, 81.7% of employability participants who have taken part in the project have progressed to positive destinations. This is an increase of 24.9% from the previous figure of 56.8%. / These destinations include employment, further education or training, returning to school or moving on to additional employability support for continued development. / The remaining 18.3% have not progressed, primarily due to leaving the programme early for various reasons, such as changes in personal circumstances or disengagement from the service.	Green	56.8%	2023-24	81.7%	2024-25		60%	62%	65%

Ref	Action	Measure	Comments	Status
A.1.2	Provide targeted support to adults facing barriers to employment	Number of people supported into training, education and employment	From April 2024 to March 2025, a total of 1,981 adults signed up to receive employability support. Additionally, some individuals who began their programmes in the previous financial year continued to receive support during this period. As such, all participants, both new and continuing, are included in the reported outcomes. During this time, 601 adults entered employment, while 277 progressed into further education or training. Those who did not achieve an outcome within this period include participants still actively engaged in their programmes and those who left early or disengaged.	Green
A.1.3	Provide a range of / employability programmes to parents through the Tackling Child Poverty funding programme	Number of parents/carers supported across the six priority groups into training, employment and education	As above, all new and continuing participants are included in reported outcomes. 448 parents/carers from the six priority groups signed up for employability support in the period April 2024 to March 2025. Within the same period, 125 moved into employment and 88 into further education and training. Those who did not achieve an outcome within this period include participants still actively engaged in their programmes and those who left early or disengaged.	Green
A.1.4	Provide specialist employability support to young people and adults with additional support needs	Number of young people and adults provided with specialist Employability Support supported into training, employment and education	As above, all new and continuing participants are included in reported outcomes. 392 young people and adults with a disability/additional support needs signed up to receive support in the period April 2024 to March 2025. Within the same period, 97 moved into employment and 40 into further education and training. Those who did not achieve an outcome within this period include participants still actively engaged in their programmes and those who left early or disengaged.	Green
A.1.5	We will work with and support people of all ages to help them re-engage with education and learning or to improve their employability skills	Learners will be offered opportunities to learn skills that meet their needs across a range of settings. We will work with learners to:- / Enhance their parenting skills / Help parents to support their child’s learning	As a result of Community Learning and Development (CLD) work delivered by the Youth Family and Community Learning Service across a range of education and community settings the following has been achieved in 2024-25: / 494 learners have enhanced their parenting skills; / 145 learners are better able to support their child during key transitions (such as from primary into secondary school); and / 157 learners are better able to support curricular learning.	Green
		We will continue to support learners to progress to other appropriate learning opportunities, ensuring that we meet ongoing needs. We will work with learners to: / Help them re-engage with education/ learning / Help them access volunteering opportunities / Help them access any other appropriate learning programmes or opportunities / Improve their employability skills	As a result of Community Learning and Development work delivered by the Youth Family and Community Learning Service across a range of education and community settings the following has been achieved in 2024-25: / 828 learners have re-engaged with education/ learning; / 378 are accessing volunteering opportunities across the service; / 623 have progressed to other appropriate learning programmes or opportunities; and / 679 learners have improved their employability skills and 111 have progressed to employment.	Green

Putting learning at the centre / We will support young people to progress to further learning, work or training when they leave school

Outcome: Young people will be supported to progress to sustained positive destinations when they leave school

				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
A.2.1	Support young people to progress to positive post-school destinations	Increase the School Leaver Destination Rate (SLDR) initial positive destination rate	3,625 young people left school in 2023-24, 96.4% of whom achieved a positive destination. This was a reduction of 0.5% from 2022-23. South Lanarkshire achieved a higher rate than the national rate of 95.7% and placed 10th of the 32 Local Authorities.	Green	96.2% / (SLC) / 95.5% / (Scotland)	2020-21	96.4% / (SLC) / 95.7% / (Scotland)	2023-24		97%	97%	97%
		Decrease the gap in the School Leaver Destination Rate (SLDR) initial positive destination rate between the most and least deprived data zones	South Lanarkshire has a gap of 3.2% which has increased slightly from 2022-23 (2.9%) and compares to 4.3% across Scotland.	Green	6.1% / (SLC) / 4.4% / (Scotland)	2020-21	3.2% / 4.3% / (Scotland)	2023-24		2.9%	3%	3%
		Increase number and percentage of looked after school leavers in a positive destination by local authority	There were 68 young people in this cohort classed as ‘care experienced’. The positive destination rate is 91.2% for this group of leavers and remains above the national rate.	Green	92.5% / (SLC) / 86% / (Scotland)	2020-21	91.2% / (SLC) / 87.2% / (Scotland)	2023-24		93%	93.5%	94%

Ref	Action	Measure	Comments	Status
A.2.2	Deliver targeted support and learning opportunities to young people in the last 6 months of school through the Aspire programme	Number of young people engaged on the programme	741 young people engaged in the Aspire programme. The Aspire programme has three options for young people to support them as they approach their school leaving date, this includes individualised one-to-one support, college-based leaver programmes and groupwork.	Green
A.2.3	South Lanarkshire Council and Skills Development Scotland will work together to track the destinations of young people aged 16-19 including regular home visits	Number of young people who did not achieve/sustain a positive destination referred to support through tracking and re-engaged	The Employability Service tracked the initial destinations of all South Lanarkshire leavers and conducted a robust tracking exercise in collaboration with Skills Development Scotland to identify and engage young people who did not achieve/sustain a positive destination. In 2024-25, 104 young people were successfully re-engaged through this tracking exercise.	Green

Our Children and Young People Thrive / We will work to ensure children have the best start in life and become everything they can be

Outcome: Every family should get the right support at the right time for as long as they need

				---BASELINE--- ---LATEST---					---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med (3yr)	Long / (10yr)
B.1.1	Four Family Support Hubs to promote a no wrong door approach and GIRFEC Pathways with community, third sector and universal pathways to be strengthened	By March 2025, there will be a 60% reduction in new referrals to Social Work Resources escalating to local office allocations	The Family Support Hubs have offered accessible provision in Hamilton, East Kilbride, Lanark and Cambuslang localities. Each area has a team of social workers, family support workers, group workers, peer workers, Children 1st staff and therapists who have offered families a wide range of different types of support with a shared remit of providing whole family support that prevents crisis, reduces inequalities and improves child development, family functioning and wellbeing. / As a result of this ‘no wrong door approach’ for families, 75% of new referrals to Children and Families Social Work were dealt with by the hubs, a 14% increase from last year (61%). A Parenting Support Group Work Pathway has been successfully implemented with key partners to ensure a coordinated approach to supporting parents through a range of evidence-based programmes and locally developed engagement based on Getting it Right for Every Child. 76% of parents who attended the Incredible Years Programme reported an improvement in their child’s strengths and difficulties score. 96% of parents who attended the ‘You and Your Child’ programme reported an improved understanding of their child’s developmental needs and how to meet these as parents. / There has been an increase in participation from fathers this year both in the Dad’s Group and across the other programmes. Across the Hubs there is a range of groups and activities available for children and young people, including group work for teens, summer activities and outdoor learning.	Green	60%	2024	75%	2024-25		60%	TBC	TBC

Ref	Action	Measure	Comments	Status
B.1.2	Family Group Decision Making as a core partner to Early Years Multi Agency Service	By March 2024, 80% of families supported will report improvement in involvement in planning supports for their children and their family	Family Group Decision Making (FGDM) is available to families at the pre-birth stage to help them find their own solutions to any challenges they are facing. This service is provided by Children First and 74 families have been introduced to FGDM this year. / The Parents Plan approach was introduced in March 2024. At this stage the average number of pre-birth investigations was 1.2 per week. It took a number of months to see a sustained shift but from December 2024 the shift below the baseline has been sustained for 14 weeks and the new average per week has reduced to 0.4, which is a 67% reduction in the number of pre-birth investigations initiated for unborn babies. / As a result of this approach, all families supported have reported improvement in support for their children and their family. Outcome scales completed with families at the beginning and the end of their engagement in FGDM indicates a 100% improvement of all outcomes. This measurement scale is used with all families engaged in the support and data is available.	Green
		Implementation of a Parents Plan to prevent escalation to child protection	The Parents Plan approach was introduced in March 2024 to provide a more whole family lens on supporting a child at the perinatal/infant stage and also to enable the views of parents to be articulated in any assessment and plan for support. At this stage the average number of pre-birth investigations was 1.2 per week. It took a number of months to see a sustained shift but from December 2024 the shift below the baseline has been sustained for 14 weeks and the new average per week has reduced to 0.4, which is a 67% reduction in the number of pre-birth investigations initiated for unborn babies.	Green
B.1.3	Continue to refine and consolidate the Pathfinders approach	By March 2025, 60% of children and young people accessing Pathfinders will report improvement across three outcome indicators	The Pathfinders Programme currently operates in six secondary schools in South Lanarkshire (Cathkin High, Stonelaw High, Lanark Grammar, Calderside Academy, / St Andrew’s and St Bride’s and Carluke High), and is supported by the Family and Community Learning Pathfinder Service. / The early and effective model of engagement has supported vulnerable young people and their families through a whole family approach and is focused on improving attachment and family relationships. The multi-agency model is helping young people achieve their best possible life outcomes, and supporting them to reach their full potential with the aim of helping to close the attainment gap. / Home visits and parental engagement have helped to keep families connected with the wider community and young people are actively engaged in ensuring that the right support is in place for them throughout the project. / Families have had a say in how Pathfinders has developed to / ensure that the work is relevant, meaningful, bespoke and holistic and that it supports each individual young person and family appropriately. / Over the past 12 months, the programme has exceeded its initial target to engage 350 young people and families, working with a total of 421 young people and families accessing support and benefiting from sustained engagement that is helping to meet identified needs. / In helping to evaluate the impact of the project, young people involved have reported that they have developed their social skills, are more able to manage negative peer influences and have improved their overall health and wellbeing.	Green
B.1.4	Test an improvement approach to support at least 10 families with children with disabilities to cope with the financial demands of having a child/children with disabilities	By March 2025, 80% of families supported report an improvement in financial wellbeing and at least one of the other targeted outcomes / Improved health and wellbeing; / Reduced social isolation; and / Increased engagement with education, training or employment	The Paths Away From Poverty project developed co-produced, person centered, needs led support plans with families, which included goals and/or aspirations in respect of support to work through barriers, difficulties and/or complexities they were experiencing. / Eight families benefited from a range of supports including regular one-to-one sessions for parents and carers, group sessions to develop peer networking and support opportunities and supported access to a range of essential services and amenities e.g. GPs, Housing providers, family support hubs, DWP, clothing and food banks, Lanarkshire Carers etc. This navigation role was a key element of the practice model in helping families access the following: / Financial wellbeing support debt and budgeting advice and new applications for various benefits; / GP and Health Services e.g. Child and Adolescent Mental Health Services (CAMHS) and occupational therapy; / Engagement with housing providers to work collaboratively on housing issues, such as rent arrears; / Local food and clothing banks; / Time out from their caring role; and / Specialist help when necessary, e.g. signposting to ‘Talk Now’ counselling to support historic trauma and ongoing poor mental wellbeing. / All families reported a reduction in financial stress and other additional outcomes e.g: / Improved quality of living within the home as a result of better access to additional resources via local authority and housing services; / Families more open and trusting of staff as a result of changes which have taken place in their lives and their children’s lives; / Parents are choosing to fully engage within their support and support from other sources e.g. school, housing etc; / Improved health and wellbeing, as a result of stronger and more trusting relationships with NHS Lanarkshire, CAMHS and local GP surgeries; / Improved confidence and motivation of parents/carers who have Additional Support Needs and being more open to engage with their local community; / Families more able to identify opportunities to connect with other community members, such as trusted neighbours, family members etc; and / Reduced isolation, due to families being supported to engage in meetings, appointments, activities and outings within their local community. / An additional three families were referred to the project but their circumstances had improved enough to not require ongoing support.	Green
B.1.5	Four Family Support Hubs to promote a no wrong door approach and GIRFEC Pathways with community, third sector and universal pathways to be strengthened	By March 2026, 80% of parents supported will report improvements in family wellbeing	The Family Support Hubs have offered accessible provision in Hamilton, East Kilbride, Lanark and Cambuslang localities. Each area has a team of social workers, family support workers, group workers, peer workers, Children First staff and therapists who have offered families a wide range of different types of support with a shared remit of providing whole family support that prevents crisis, reduces inequalities and improves child development, family functioning and wellbeing. / Across the Hubs there is a range of groups and activities available for children and young people, including group work for teens, summer activities and outdoor learning. / There has been an increase in participation from fathers this year both in the Dad’s Group and across the other programmes. / As a result of this ‘no wrong door approach’ for families, 75% of new referrals to Children and Families Social Work were dealt with by the Hubs, a 14% increase from last year. / A Parenting Support Group Work Pathway has been successfully implemented with key partners to ensure a coordinated approach to supporting parents through a range of evidence-based programmes and locally developed engagement based on Getting it Right for Every Child. / 76% of parents, who attended the Incredible Years Programme, reported an improvement in their child’s strengths and difficulties score and 96% of parents who attended the You and Your Child programme reported an improved understanding of their child’s developmental needs and how to meet these as parents.	Green
B.1.6	Health and Social Work to work collaboratively with parents to identify strengths and areas for improvement in relation to neglect	Number of families completing the neglect toolkit by March 2025	The implementation of the ‘Working with Neglect Practice Toolkit’ in South Lanarkshire has been in progress over the past 2½ years, with training being a part of the implementation. / Responding to Neglect training continues to be available within the Public Protection Learning and Development Programme, with 3 sessions delivered each year. Going forward, the training will move from virtual Microsoft Teams to face-to-face delivery. / In total, 199 frontline staff and managers from Social Work, Health, Education and the Third Sector have completed the Responding to Neglect training.	Green

Our Children and Young People Thrive / We will work to ensure that the health and wellbeing of children, young people and families is improved

Outcome: Every child and young person should be able to access local community services which support and improve their mental health and wellbeing

Ref	Action	Measure	Comments	Status
B.2.1	Deliver one Mellow Bumps Pregnancy Session in each locality in partnership with the Family Support Hubs	By March 2024, 80% of participants in the Mellow Bumps Pregnancy Sessions will report increased knowledge and understanding about stress, anxiety and self-care	Sixteen parents completed the Mellow Bumps programme, which is having a positive impact on families’ wellbeing and is helping to build stronger relationships with those who are less likely to access universal services. The programme is helping to develop social connections through meeting other mums-to-be and learning about infant development and how to support it. Feedback from participants has been positive, with all mums-to-be reporting feeling better about themselves and at least two thirds telling us the programme had helped identify their personal strengths and build positive bonds with their baby. Participants said that the group provided support and practical strategies to help them connect with their bumps.	Green
B.2.2	Create and implement training at informed level to be delivered to Children’s Services staff through a Learn Online module	By March 2024, at least 50 Children’s Services staff will have accessed the Learn Online module and reported an increase in confidence in supporting children and young people at risk of self-harm and suicide	The learn online module is now in place. / Further to discussions, it was agreed that this should not be a generic module for all Children’s Services staff and should be more targeted. School counsellors were identified due to the role they play in supporting children and young people within an education setting. An adapted, online module of the training was provided and targeted at this group. / Training invites were sent to all school counselling providers within South Lanarkshire. In response, five out of six counselling providers sent their school counsellors to attend the training. 32 out of a possible 44 school counsellors took part (73%).	Green
B.2.3	Key members of staff who support children and young people at risk of self-harm and suicide to attend Lifelines Lanarkshire training	By March 2024, at least 75% of staff who have attended Lifelines Lanarkshire training have shown an increase in confidence supporting children and young people at risk of self-harm and suicide following the training	Lifelines Lanarkshire multi-agency guidance training was provided for key staff to learn about Lifelines Lanarkshire and how to use the guidance to provide support to children/young people they may be in contact with within their role. / A need was identified to focus on school counsellors, due to the role they play in supporting children and young people within an education setting. An adapted, online module of the training was provided and targeted at this group. / Training invites were sent to all school counselling providers within South Lanarkshire. In response, five out of six counselling providers sent their school counsellors to attend the training. 32 out of a possible 44 school counsellors took part (73%). / As a result, the training helped to raise awareness of staff about self-harm and suicide and increase their confidence about how to talk about self-harm and suicide. / Of the staff participating, 65% reported increased knowledge, understanding and confidence in self-harm and suicide. 96% highlighted an increase in confidence regarding using the Lifelines Lanarkshire guidance materials.	Green
B.2.4	Continue roll out of Kooth service and increase the use of this	By March 2024, at least 80% of registered users will report Kooth is effective in supporting them with their emotional wellbeing needs	The Kooth digital platform helps young people to access emotional wellbeing support and therapy through a peer community and professional support approach. South Lanarkshire children and young people are actively engaged and using all aspects of the platform. Between April 2024-March 2025, 678 young people accessed Kooth with 72% of them reporting that the platform content was a useful form of support.	Green

Our Children and Young People Thrive / We will work to ensure that the life chances of children and young people in need of care and protection are improved

Outcome: Children and young people should grow up loved, safe, respected and listened to

Ref	Action	Measure	Comments	Status
B.3.1	In conjunction with care experienced young people develop ways that make it easier for them to participate in the ongoing improvement in key decision-making processes and capture the impact of their views and voices	70% of care experienced young people tell us that they feel more able to participate in key decision-making processes	A new suite of documents has been completed for use and have been designed by care experienced young people using trauma informed language. / The paperwork was benchmarked with Promise colleagues from different local authorities coming together to review its use e.g. outcomes and attendance at planning and review meetings for looked after children. The ‘team around the child’ professionals have reported increased attendance, improved participation as well as a better understanding of the layout. 100% of children and young people report they are more able to participate in key decision making processes as a result. / The Champions Board members have now met with Corporate Parents on a regular basis including the council’s Chief Executive and other key decision makers. / The ‘Champions’ have provided feedback advising that they collectively feel more included, consulted and more able to influence change at varying levels such as the ‘Keeping The Promise Thematic Group’, with the Housing Planning Group and Health Services. / ‘Mini Champs’ groups have been established in all secondary schools and are supported by the Promise Development Team and care experienced teachers to ensure that the voices of care experienced pupils are heard.	Green
B.3.2	Support young people from 16 years old to actively manage their Child Trust Fund and/or Junior ISA savings account currently administered by the Share Foundation	70% of young people report they are better informed about financial planning	Within three months of their 16th birthday, all care experienced young people are issued with a letter from the Share Foundation (via their social worker) informing them of their rights to take charge of their Child Trust Fund and how to do it. A number of partners are supporting the process of making care experienced young people aware of the trust funds and junior ISAs and their benefits. These include / Social Work staff, Family Connections Team, Secondary Schools, the Champions Board and the Community Engagement Team (via the Financial Inclusion Network). / Social Workers provide support to the young person undertaking the process of claiming their trust fund. The Continuing Care and Aftercare team support the council’s relationship with the Share Foundation and its relevance to the young people they support. / Progress has been made in identifying groups of young people who could potentially ‘slip through the net’. The Family Connections Team are involved with tracing and contacting those young people who no longer have any social work involvement but whose trust fund remains with the Share Foundation. Schools are also being asked to help trace young people with trust funds, who do not have social work involvement. / In addition, some young people have been supported to engage with the Stepladder Plus programme, which can earn them up to £1,500 (to be deposited in their trust fund) upon completion of all its stages. This programme is open to 15-17 year olds and is run by the Share Foundation. So far, £14,750 has been earned by 14 young people, including 8 who have received the maximum amount. All the young people who have participated in the support programme report that they are better informed about financial planning.	Green
B.3.3	Meet housing needs through continued development of Person-Centred Pathway Planning	By March 2024, 100% of young people will have a Person-Centred Pathway Plan	This action is now complete and the implementation of this work ensures that 100% of young people who need it have a Person-Centred Pathway Plan in place to support their housing needs. / This work is being further informed by a Housing led test of change called ‘SLC Futures’ in partnership with other council resources and Barnardos, which has successfully supported six young people into training flats with two young people receiving settled tenancies by year end of support and a further four young people supported through outreach services. / Some output examples: / Throughcare Protocol implemented and 3 sessions with Champions Board members completed. / 44 new Throughcare Applications received during 2024-25. / 49 active applications as at the end of March 2025. / 43 Throughcare Young People housed as at the end of March 2025. / This work is now embedded in the offer of Throughcare and After Care Support.	Blue
B.3.4	Test the Throughcare Mental Health Pathway is offering the correct level of support for those with low and medium need	By March 2024, 75% of young people have been offered a low or medium need mental health support, report it has improved their mental wellbeing	Test of the Throughcare Mental Health Pathway concluded at the end of March 2024, with a sustainable model being progressed through the School Nursing Team. 102 referrals were made between August 2022 - March 2024 (average 3.6 per month). Of these, 75% engaged with the service and 63% reported that the support has improved their mental wellbeing. This work is now embedded in the work of the School Nursing Team.	Blue
B.3.5	Provide targeted support to care experienced young people to engage and sustain participation in South Lanarkshire Local Employability Partnership (SLLEP) funded employability programmes	By March 2024, establish a baseline percentage of care experienced young people engaging with SLLEP funded employability activity progressing to a positive destination	A baseline of 65% was established in March 2024. In 2024-25 this target has been exceeded. 91 care experienced young people engaged with employability services, 86.8% progressed to a positive destination. A breakdown of the destinations is as follows: / Employment/Modern Apprenticeship – 8. / Further/Higher Education – 45. / Progression to next stage Employability support – 26.	Green

Thriving businesses and fair jobs / We will work to make sure everyone has the same opportunities to learn new skills

 ----
Outcome: People experiencing barriers to employment are supported into sustainable work B -	=
				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
C.1.1	Work with employers to progress people to employment	Number of employability participants progressing to employment	The number of employability participants progressing into employment has increased this year by 16.3%.	Green	623	2023-24	725	2024-25		625	650	700

Ref	Action	Measure	Comments	Status
C.1.2	Deliver sector-based training to employability participants	Demand led sector-based training will be delivered to meet the needs of the Labour Market	The Local Employability Partnership Operational Sub-Group met throughout the year to identify need across employability caseloads and agree provision to be delivered. Training has included construction tasters, hair and beauty tasters, QTS Rail Academy, Construction Skills Certification Scheme (CSCS) cards and Social Care.	Green
C.1.3	Provide in-work support and training through the Upskilling programme	Number of employed people engaging with the Upskilling programme	19 parents have engaged on the Aim to Achieve (Upskilling programme) and accessed in-work training. For 2025-26 the programme will merge with Supporting Families and in-work support will be provided as part of a wider parental employability approach.	Green
C.1.4	Work with employers to identify vacancies for progression for employability participants	Number of new employer engagement contacts developed and vacancies filled	Across South Lanarkshire Council and our partners, Routes to Work South, we have engaged with and provided support to 524 employers, actively managing and filling 392 vacancies with clients from across all our employability programmes.	Green

Thriving businesses and fair jobs / We will ensure that the place where you live is at the heart of our response to the climate emergency and help places to become sustainable

 ----
Outcome: Thriving town and neighbourhood centres provide a focal point for local communities B -	=
Ref	Action	Measure	Comments	Status
C.2.1	Deliver the town centre masterplans for East Kilbride and Hamilton whilst continuing to support South Lanarkshire town centres over the next 10 years, and a series of town specific strategies and action plans will sit below this, giving a template for placemaking within our communities	Monitor and deliver town centre measures and initiatives in line with town strategies, Community Wealth Building and 20 Minute Neighbourhood approaches. / Town Centre Vacancy Rates – maintain at or below national averages / Businesses supported (including Social Enterprise) – support across towns and places	Both masterplans are progressing well. A Project Management (PM) Team has been appointed to help deliver the East Kilbride Masterplan and £50.3m of funding has been secured. Working towards demolition of Centre West, delivery of a new Civic Hub and residential development. / £8m has been secured towards the delivery of the Hamilton Masterplan. A list of suitable projects to take the plan forward has been drawn up and will go to council committee in August 2025. A PM Team will also be appointed for Hamilton Town Centre shortly and plans are progressing well for the town square development. / Town Centre Vacancy Rates sit, in general, below the national average with the exception of East Kilbride and Hamilton. Both of these town centres have an over-supply of retail which is being addressed by the masterplans. / With a commitment to rebalance the town centres away from an over-reliance on retail, the masterplans seek to forge a community focused future, fostering connectivity, liveability and economic vitality for generations to come.	Green

Thriving businesses and fair jobs / We will make it easy for businesses and social enterprises get all available help and advice from one place

 ----
Outcome: South Lanarkshire is an attractive place to start, grow and locate a business B -	=
				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
C.3.1	Number of new South Lanarkshire business starts supported by Business Gateway / (Locally set target)	Total number of businesses/social enterprises supported / New start-ups	Over 2024-25, the council’s Business Support to new start-ups delivered under the Business Gateway (BG) brand supported 907 unique start-up businesses. From February 2024, and following an options appraisal, the BG contract was brought in-house in February 2024 and is managed and delivered by North Lanarkshire Council as lead for BG across the whole of Lanarkshire. The Business Gateway have access to several locations in South Lanarkshire where BG staff can operate from to ensure reach and accessibility to businesses/ social enterprise across South Lanarkshire.	Green	500	2023-24	907	2024-25		500	N/A	N/A
C.3.2	Number of business support interventions per annum by Economic Development (grants, loans or advice) / (Locally set target)	Total number of businesses/social enterprises supported / Existing / Organisations	The business model of how South Lanarkshire Council (SLC) delivers client facing business support changed during this year and now rely on Business Gateway to deliver face-to-face advice to South Lanarkshire Businesses. / This had an impact on the number of interventions that SLC can support this year and will going forward. / Although SLC and North Lanarkshire Council (NLC) manage the Business Gateway contract, SLC still offer grants and advisory support such as the SLC Property Advice Service and Supplier Development Programme.	Red	1,200	2023-24	1,014	2024-25		1,200	N/A	N/A
		Number and value of grants	62 business grants were awarded in the 2024-25 reporting year. / South Lanarkshire Council’s (SLC) Business Grant Fund totaled £500,000 in the year 2024-25. These funds were supported by the UK Government via the UK Shared Prosperity Fund. / This figure when added to the amount spent on grants in the previous year is £995,986.44. / This equates to a shortfall over the two years of £4,013.56, where SLC were allocated £1,000,000 (£500,000 per financial year) for Business Grants.	Red	£723,000 / (Made up of European / Regional / Development / Fund projected. / £483,000 / Plus / £180,000 SLC monies, plus / £60,000 UK / Shared / Prosperity / Fund)	2023-24	£501.051	2024-25		£723,000	N/A	N/A
		Grants awarded to businesses/social enterprises / Funding / leveraged	This figure equates to the amount of private sector contributions made by applicant businesses to our Business Growth Grant. / All of the council’s current Business Grants require private match funding from the applicant. This information is required from all applicant businesses, and this detail will continue to be sought.	Green	N/A	N/A	£490,385	2024-25		N/A	N/A	N/A
		Total number of jobs / Jobs safeguarded	The total figure of jobs created and sustained is 528, which exceeds the set target of 500.	Green	500	2023-24	528	2024-25		500	N/A	N/A
		Total number of jobs / Jobs created	The total figure of jobs created and sustained is 528, of which 53 are new jobs that have been created, which exceeds the set target of 500.	Green	Included in above baseline data figure as overall target -jobs created/ sustained	2023-24	53	2024-25		N/A	N/A	N/A
		Total number of jobs / Increase in / Turnover/Sales	This figure is taken from Business Grant applications and demonstrates the significant positive impact our grant scheme has on supporting local businesses, and in particular, the growth aspirations of the businesses. / The increase in turnover and sales is £8,532,339.	Green	N/A	N/A	£8,532,339	2024-25		N/A	N/A	N/A

Caring, connected communities / We will continue to support and encourage every community to identify and act on their local priorities

        Outcome: Communities feel empowered to identify and act on their local priorities

Ref	Action	Measure	Comments	Status
D.1.1	Ensure communities are engaged and supported to participate in local decision making	Develop standards and a framework for the planning, delivery and evaluation of place based Participatory Budgeting programmes	A Participatory Budgeting (PB) Community Advisory Group has been established to help develop a basic toolkit/rule book for PB across the ten Neighbourhood Planning areas. This group will work alongside established Our Place Our Plan (OPOP) and Neighbourhood Planning groups to ensure that PB processes are robust and fit for purpose. Identifying areas for improvement is also a fundamental priority of PB.	Green
		Strengthen the Neighbourhood Planning and Participatory Budgeting approach by co-producing standards and a framework for the involvement of young people	Work is ongoing with Our Place Our Plan (OPOP) Stakeholder Groups, and other Neighbourhood Planning groups, to develop bespoke approaches and opportunities, to ensure young people have a voice in the Participatory Budgeting (PB) process. Focus groups are also being held in partnership with youth service providers to increase the work of the PB Community Advisory Group.	Green
D.1.2	Fulfil statutory Locality Planning duties to reduce inequalities within identified priority neighbourhoods	Work with local communities in the area of / East Kilbride South to identify local priorities and prepare a Neighbourhood Plan for their area	The East Kilbride South Neighbourhood Plan is in development. Initial engagement from local residents, community views and engagement with young people from local schools has taken place and data analysis is in process. / Development of the Stakeholder Group has been a priority to build capacity. The local library and community hall were listed at risk of closure in spring/ summer 2024 which are assets that are highly referenced in the community feedback. This situation became a catalyst for increasing community engagement and for the local community to come together. The Stakeholder Group understood this is a priority for the local community and would like to ensure the assets are opened by local organisations before proceeding into further community action planning workshops and events. / A Participatory Budgeting event has been held by the Stakeholder Group with Third Sector partner Healthy & Active hosting the funds with £7,000 funding awarded to 8 local groups. A total of 3,480 votes were cast from 1,160 people.	Green
		Evaluate the Neighbourhood Planning approach for South Lanarkshire and implement improvement actions	Evaluations are planned in the more established Neighbourhood Planning areas, beginning in Strutherhill and Birkenshaw. Learning from this will be used to support a roll-out in Hillhouse, Udston and Burnbank, and Springhall and Whitlawburn. The other seven Neighbourhood Planning areas will follow.	Green
D.1.3	Ensure children’s rights and awareness of the United Nations Convention on the Rights of the Child (UNCRC) is embedded in the work of partner organisations	Develop a UNCRC webinar to support the understanding of children’s rights and the UNCRC across the CPP workforce	The UNCRC webinar, designed with young people and funded through the Community Planning Partnership (CPP), is now complete and accessible to all partners via the Fusion Learning and Development platform. External partners can access via a link. / Partners have been informed of availability via the Children’s Services Partnership structures and the CPP Progress Group. Partners have been asked to encourage all staff to complete the webinar as part of staff awareness of the UNCRC. / This forms part of the commitment to implementing the requirements of the UNCRC (Incorporation) (Scotland) 2024.	Blue

Caring, connected communities / We will bring communities together to share priorities and work jointly on them

        Outcome: Communities feel connected, share priorities and work together to create change

Ref	Action	Measure	Comments	Status
D.2.1	We will bring communities together to share priorities and work jointly on them	Continue to develop and strengthen the membership of the Hamilton and East Kilbride Community Partnerships	In the Hamilton and East Kilbride Community Partnership areas, efforts are still being made to increase membership and capacity through ongoing engagement with community groups and partner agencies. It has been agreed that chairs are required for both the Hamilton and East Kilbride Community Partnerships. / There are still opportunities to find and encourage new members to participate in the Community Planning Partnerships through regular Neighbourhood Planning meetings.	Green
		Evaluate the Community Partnership approach with Cambuslang and Rutherglen and Clydesdale Community Partnerships and implement improvement actions	The Community Partnership self-evaluation survey results and comments have been finalised. The feedback received was analysed and this knowledge has assisted in reviewing future objectives, creating improved procedures, supporting training requirements and assessing process change whenever possible.	Green

D.2.2	Young people will lead the way on actions to tackle climate change and nature loss	Support young people to continue to develop their leadership skills through engagement with the Community Planning Partnership Strategic Board on their Climate and Nature priorities	A Development Session was planned by members of the South Lanarkshire Youth Forum on Climate Change and Sustainability and delivered to the South Lanarkshire Community Planning Partnership Board on 23 October 2024. / Members identified 3 key priorities for exploration with the Board members, the priorities being a Walk to School campaign, Uniform recycling and Community litter picks. The inputs and discussion supported the Board’s understanding of the challenges facing communities and the young people in their efforts to affect change. Support from the Board helped young people to consider practical ways to progress their ideas such as the council’s support to equip and guide young people in organising localised community litter picks such as the 3-week campaign by Duncanrig High School, involving over 350 S1 pupils in litter picking across their communities. In addition to this, the Board were able to support the Youth Forum prepare for their third, council wide environment event for schools, by helping visit Whitelee Windfarm to inform their planned ‘Power Up: Understanding renewable energy’ session at the Convention of Schools (COS) 3 event from 26-28 March 2025, seeing over 300 P5-P7 pupils in attendance. / The Development Session and ongoing support from the Board is helping both young people and Board members to continue to refine their understanding of environmental issues and ideas towards mitigating and adapting to the impacts. / As a result of this engagement, young people report that their confidence continues to grow as they take on more leadership roles in the development and delivery of actions to tackle climate change and nature loss.	Green
		Increase youth voice and influence in Community Planning at a locality level through co-producing an approach to youth participation	A working group of identified services engaged in developing and progressing youth voice across communities has continued to meet to maximise opportunities for young people to engage in decision making and raising issues. Recent success has resulted in over 1,200 young people engaging with the South Lanarkshire Council budget consultation 2025-2026, with young people assisting their peers to participate. With the Marmot Place Programme now initiated in South Lanarkshire, further work is being undertaken to capture best practice across youth engagement work towards ensuring young people are knowledgeable and confident to engage in influencing their communities, consistently and effectively.	Green
D.2.3	Empower communities to improve their own health and wellbeing	Progress the implementation of the South Lanarkshire Age Friendly approach through the development of an implementation plan and supporting the Seniors Community to develop and deliver on actions	Three focus groups were held with the community of older people during October 2024 to consult on the World Health Organisation’s (WHO) Checklists for Age Friendly Cities. This assisted older people to prepare an Engagement Report on their view of these standards and to add any required to be included. This was shared with Community Planning Partnership (CPP) members. / A CPP Workshop was held on 22 April 2025 which will consider the next step towards the development of an Implementation Plan. This will also see South Lanarkshire Council move into stage three of the four stage programme of developing an Age Friendly Community.	Green

Caring, connected communities / We will involve local representatives in community planning at all levels, including on the Community Planning Partnership Board

        Outcome: Community volunteers feel that they can effectively participate in and contribute to community planning at all levels
 People Thrive
Ref	Action	Measure	Comments	Status
D.3.1	Develop and deliver training/awareness raising activity to ensure that volunteers can participate effectively in Community Planning	Increase the number of volunteers in our Neighbourhood Planning Stakeholder Groups who feel confident about their role in Community Planning through capacity building, training and support	Increasing the number of residents participating in the Our Place Our Plan (OPOP) Stakeholder Groups is ongoing and a range of engagement approaches have been developed to ensure wide and representative involvement. / Building social capital is the cornerstone of Neighbourhood Planning. The OPOP Stakeholder Groups continue to act as a catalyst to empower and build the capacity of local people. The use of an asset-based approach to Neighbourhood Planning is helping build community confidence and aspiration. / Delivering the Neighbourhood Plans has created opportunities for increased local decision making, partnership working and greater collaboration between local people and those providing services. This is helping to consolidate the understanding of the participants role and influence around the work of the Community Planning Partnership partners and Community Planning.	Green
		Increase the number of volunteers in our established locality Community Partnerships who feel confident about their role in Community Planning through capacity building, training and support	Over the course of the year, membership of the Cambuslang and Rutherglen and Clydesdale Community Partnerships has remained consistent. With the Community Planning Partnership’s Community Development Officer (CDO) attending wider council-led community meetings, new chances to identify more members have emerged across communities. / To support and identify any learning or training opportunities required to develop and comprehend the needs and devise a plan to implement these activities, the CDO is continuing to work with all Community Partnerships. Currently under consideration is the process for making the Community Planning Partnership volunteer friendly.	Green
		Train 12 employees/community representatives as Health in the Community (HIIC) Trainers and support them to achieve accreditation	HIIC is a course that helps people understand what affects their health and the health of their communities and assists people of all ages to develop the skills and knowledge to address health issues using community development approaches. / HIIC Tutor Training, which was facilitated by the Scottish Community Development Centre (SCDC), took place on 20 and 21 February 2024 and delegates were asked to undertake practical assignments to be completed by August 2024. / 12 employees/community representatives completed this training and 4 have submitted their portfolios, passed their assignments and become accredited facilitators. Other participants have either left their post or moved to a new role.	Green
		Increase community representation on the Community Planning Partnership Strategic Board and provide youth voice opportunities	To increase membership in all localities and locate people who would like to represent or chair / existing partnerships moving forwards, the Community Planning Partnership’s (CPP) Community Development Officer has worked collaboratively with council officers and various CPP partners. / The Hamilton and East Kilbride Community Partnerships are currently being established. It is proposed that chairs for each of these Community Partnerships be confirmed once governance arrangements and future priorities have been finalised. / Discussions have taken place to provide youth voice opportunities. A mapping exercise will be carried out to identify all current youth engagement and participation activities across the partnership and this will be reported to the CPP Board at a later date.	Green
D.3.2	Upskill employees in participation and engagement approaches	Increase the number of employees who feel more confident in securing the participation and engagement of individuals and communities in their work	Two engagement webinars are now complete and accessible to all partners via the Fusion Learning and Development platform. One webinar focuses on the role of staff, while the other is designed to appeal to community members. External partners can access via a link. / Partners have been informed of the availability of the training via the Children’s Services Partnership structures and the CPP Progress Group. Partners have been asked to encourage all staff to complete the webinar as part of staff upskilling on engagement approaches.	Blue

Good quality, suitable housing for everyone / We will increase affordable housing supply and improve access to and choice of housing options that suit people’s needs

        Outcome: Increase overall housing supply and improve access to, and choice of housing options, that suit people’s needs and are affordable

				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
E.1.1	Deliver the council’s Home+ Programme	Increase the number of council homes in South Lanarkshire by 1,300	The Strategic Housing Investment Plan (SHIP) sets out affordable housing development priorities across South Lanarkshire during a five 5-year period. / The SHIP report to the council’s Housing and Technical Resources Committee in November 2024, noted that due to a range of circumstances, including a reduction in government funding, the council is no longer on track to meet the 1,300 target. Work will continue to focus on optimising delivery of new homes. / 503 additional council homes have been provided between 2022 and March 2025 (154 new build properties and 349 acquisitions). / In 2024-25, 180 additional homes were provided, consisting of 50 new build properties and 130 acquisitions.	Green	0	2022	503	2022-25		N/A	N/A	N/A
		Maintain the percentage of tenants in council new build properties who are satisfied with their home	This measure has been achieved. 109 tenants across nine new build housing sites were surveyed with a 61% response rate. Based on the responses received, a 99% satisfaction rate was recorded.	Green	91%	2022-23	99%	2023-24		91%	91%	91%
E.1.2	Provide settled accommodation to households experiencing homelessness	Achieve the annual Local Letting Plan target for social rented properties allocated to homeless households	The 2024-25 annual target for lets to the Urgent Housing Need list, comprising majority homeless households, has been achieved.	Green	55%-65%	2023-24	65.5%	2024-25		55-65%	TBC	TBC

Ref	Action	Measure	Comments	Status
E.1.3	Develop and implement the Strategic Housing Investment Plan (SHIP)	Annual approval of SHIP by Housing and Technical Resources Committee	The Strategic Housing Investment Plan (SHIP) / 2025-2030 was approved by the council’s Housing and Technical Resources Committee on / 27 November 2024. / The SHIP includes projects with a total potential capacity for delivering up to 1,995 affordable homes in South Lanarkshire over the 5-year period. This includes 1,665 new build homes and 330 acquisitions.	Green
E.1.4	Develop and implement Local Letting Plans (LLP) with proposed annual targets	Annual approval of LLP targets by Housing and Technical Resources Committee	LLP 2025-26 targets, incorporating lets to homeless households, were approved by the council’s Housing and Technical Resources Committee on / 26 February 2025.	Green

Good quality, suitable housing for everyone / We will work in partnership to improve housing quality and energy efficiency, whilst supporting a just transition to decarbonisation

        Outcome: Improve housing quality and energy efficiency whilst supporting a just transition to decarbonization

				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
E.2.1	Improve overall energy efficiency of homes across South Lanarkshire	Increase the average Standard Assessment Procedure (SAP) score of all homes with an Energy Performance Certificate in South Lanarkshire	This measure has been achieved. Based on Home Analytics Database, the average SAP score has increased as a result of the installation of energy efficiency and decarbonisation measures.	Green	65.1	2021-22	67	2024-25		Increase by 1% from baseline	70	TBC
		Increase number of energy efficiency and decarbonisation measures installed across private homes in South Lanarkshire utilising national funding sources	Area Based Schemes are funded by the Scottish Government and coordinated by councils to provide energy efficiency measures to homes within a local authority area. / In 2024-25, through the Area Based Schemes in South Lanarkshire there were 293 measures installed, comprising of external wall insulation, cavity wall insulation, cavity extraction and refill, loft insulation and solar PV and batteries.	Green	N/A	N/A	293	2024-25		200	600	TBC
		Increase number of energy efficiency and decarbonisation measures installed in council homes in South Lanarkshire	The council continues to deliver its Housing Investment Programme to improve the energy efficiency of its properties and reduce energy costs for tenants. / 95.63% of council stock meet the Scottish Housing Quality Standard (SHQS), this equates to 24,789 properties. / The council awaits guidance from the Scottish Government on the new social housing net zero standard.	Green	N/A	N/A	Year End 2024-25	2024-25		100 per year	TBC	TBC

Ref	Action	Measure	Comments	Status
E.2.2	Support the delivery of schemes to improve energy efficiency in homes across South Lanarkshire	Develop and implement the Energy Company Obligation (ECO) Scheme	The ECO scheme is a government energy efficiency scheme designed to tackle fuel poverty and help reduce carbon emissions. The scheme works by placing an obligation on energy suppliers to deliver energy efficiency measures to low income, fuel-poor and vulnerable households. The scheme was launched in South Lanarkshire in July 2023. / In 2024-25, 295 measures were installed in 102 private sector homes across South Lanarkshire, improving the energy efficiency of the homes and reducing energy consumption rates for occupiers.	Green
		Co-ordinate Energy Efficient Scotland: Area Based Scheme funding (EES:ABS)	The council continues to make effective use of funding to support owners to improve energy efficiency. This includes features such as external wall, cavity and loft insulation as well as solar panel and battery installations.	Green

Good quality, suitable housing for everyone / We will work in partnership to prevent and significantly reduce homelessness and improve outcomes for those at risk of or who experience homelessness

        Outcome: Prevent homelessness and improve outcomes for those at risk of or who experience homelessness

				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
E.3.1	Deliver Housing Options Service with the aim of preventing homelessness	Increase the percentage of Housing Option interventions where homelessness is prevented	During 2024-25, 60% (889) homeless household cases were prevented, broadly similar to the position recorded last year. The operating context in relation to the prevention of homelessness remains extremely challenging. The prevailing socio-economic conditions continue to adversely impact upon the ability to prevent homelessness during 2024-25. This trend has been mirrored nationally.	Red	73.5%	2021-22	60%	2024-25		70%	TBC	TBC
		Increase the percentage of former homeless households provided with a council tenancy that maintain their home for more than 12 months	Tenancy sustainment has remained strong again this year and the target has been achieved.	Green	88%	2022-23	91.9%	2024-25		TBC	TBC	TBC
		Reduce repeat instances of homelessness	Instances of repeat homelessness have increased by 15% from 98 cases in 2023-24 to 113 in 2024-25. This has resulted in performance being slightly above the target of 3%. / All repeat homelessness cases are reviewed to identify patterns and to inform future development and delivery of services.	Amber	4.5%	2021-22	4.6%	2024-25		3%	TBC	TBC

Ref	Action	Measure	Comments	Status
E.3.2	Improve access to settled accommodation to homeless households	Continue to implement the Rapid Rehousing Transition Plan (RRTP)	The final annual review of the five-year Rapid Rehousing Transition Plan (RRTP 2019 to 2024) was reported to the council’s Housing and Technical Resources Committee on 18 September 2024. The report noted the sustained and significant increase in demand from homeless households over the last two years and the challenges this has presented for homelessness services both locally and nationally. The report also sought approval for the implementation of the Homelessness Strategic Plan, to replace the RRTP.	Blue

People live the healthiest lives possible / We will ensure that all of our services work with people as early as possible to stop problems happening

        Outcome: People are able to look after and improve their own health and wellbeing and live in good health for longer

				---BASELINE---			---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data		Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
F.1.1	We will continue to support people to improve their own health and wellbeing and exercise choice and control	Number of people participating in a co-produced Self Directed Support Assessment to exercise choice and control over their care	3,756 co-produced assessments have been approved exceeding the annual target of 3,000 assessments.	Green	2,984	2022-23		3,756	2024-25		3,000	3,100	3,200

Ref	Action	Measure	Comments	Status
F.1.2	We will continue to establish a Community Led Support approach to promote to promote positive health and wellbeing outcomes and community resilience	Number of employees trained in Community Led Support approach across all localities	64 employees have been trained to promote positive health and wellbeing across localities. The Health and Social Care Partnership (HSCP) has been working with the National Development Team for Inclusion to support Community Led Support (CLS) development across the partnership. / Development sessions were held in all localities to evaluate progress made to date and share good practice. Each locality brought together a range of stakeholders, including Health and Social Care staff, Third Sector Organisations and organisations delivering key services across South Lanarkshire communities. / Over 130 participants shared their experiences and examples highlighted have been the development of Clydesdale in Conversation (CLiC), Spaces to Talk and the development of a pop-up outreach ‘Wellbeing Wagon’ in Clydesdale. In East Kilbride, strong CLS initiatives are in place through Connected East Kilbride in Calderwood, Greenhills and The Murray with the plan to establish a CLS hub in Greenhills with Loaves and Fishes. In Hamilton there is good CLS activity in community cafes and multi-agency hubs with the development of a hub in Burnbank now progressed. In Rutherglen and Cambuslang a first pop up hub is scheduled to take place. CLS hubs are now operational in each locality.	Green
F.1.3	We will promote self – care and self-management including technology enabled care	Increase in the number of people supported by Technology Enabled Care to manage their own health and wellbeing	The Technology Enabled Care (TEC) Team continues to lead the delivery of innovative, person-centred digital health and care solutions. Through its three core programmes, Telecare, Telehealth and Innovation and Solutions, the team supports citizens to live independently, safely and with greater control over their health and wellbeing as well as exploring new ways of working. Telehealth Services have continued to expand with 3,667 patients using remote monitoring to self-manage their health, an increase of 7% from the previous year. Three new remote health pathways were introduced, with a further three in development. / The ‘Near Me’ video consultation platform facilitated over 25,500 virtual appointments, saving patients an estimated £150,000 in travel costs. The number of virtual waiting areas increased to 251 and 12 ‘Near Me Near You’ community access points now support individuals without digital devices at home. / In 2024-25, 16% of hospital discharges were supported via the Home First pathway, with essential telecare installations completed within 24 hours. Over 6,000 service users have now been successfully migrated from analogue to digital alarm systems, with the remaining 500 users scheduled for transition by July 2025, well ahead of the national BT digital switchover deadline of January 2027. South Lanarkshire now operates a fully end-to-end digital alarm estate. / The digital infrastructure enables a shift towards proactive, data-driven care, supporting early intervention for individuals at higher risk of adverse outcomes. In parallel, the team’s sustainability efforts have resulted in the reuse of 1,874 alarms, generating cost savings of £314,832 and reducing environmental impact.	Green

People live the healthiest lives possible / We will increase access, activities and supports that help improve mental health and addictions

 Outcome: People, including those with disabilities or long-term conditions, or who are frail, are able to live as far as reasonably practicable,
 independently and at home or in a homely setting in their community

				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
F.2.1	We will continue to protect adults at risk from harm	Percentage of statutory supervising officer visits completed within timescale for local authority welfare guardianship orders	There was a total of 243 local authority guardianship visits due with 91% (220) being completed in time, exceeding the annual target of 75%.	Green	93%	2022-23	91%	2024-25		75%	75%	75%
		Percentage of statutory supervising officer visits completed within timescale for private welfare guardianship orders	There was a total of 2,214 private guardianship visits due with 87% (1,932) being completed in time, exceeding the annual target.	Green	93%	2022-23	87%	2024-25		75%	75%	75%

Ref	Action	Measure	Comments	Status
F.2.2	We will continue to protect adults at risk from harm	Implement Medication Assisted Treatment (MAT) standards across all localities	Medication Assisted Standards (MAT) are a set of nationally agreed evidence-based standards to enable the consistent delivery of safe, accessible, high quality drug treatments across Scotland. They were produced in response to the emergent public health crisis by the Drug Death Task Force. The standards are relevant to people and families accessing or in need of services and Health and Social Care staff responsible for the delivery of recovery orientated systems of care. / The timescale for implementation of the MAT standards is 2026. Strong progress is being made to implement the ten MAT standards. Five standards are green, three are provisionally green and one amber. While MAT standard 7 is currently red there are steps in place to progress.	Green

People live the healthiest lives possible / We will provide high quality day-to-day health and social care services that are accessible to everyone in our community who needs them

        Outcome: Health and Social Care Services are centred on helping to maintain or improve the quality of life of people who use those services

Ref	Action	Measure	Comments	Status
F.3.1	Implement Discharge Without Delay to return people to their home or community safely	Embed Home Assessment Team approach across localities to optimise independence of those discharged from hospital/prevention from hospital admission	In 2024-25, care packages were reduced on average by 29% following Home Assessment Team (HAT) intervention. In the same period, the service supported over 1,000 episodes of care, and 50% of service users who completed HAT intervention either required, reduced or no support following intervention. Performance has fallen slightly, short of the 30% annual target, however, it is acknowledged performance has been variable across the period and is influenced by the volumes of individuals with complex needs being supported by the service who have little or no reablement potential. A review of the service model and criteria for the service is currently underway which is expected to result in changes to pathways, increasing the flow and capacity through HAT which will have a positive impact on performance going forward.	Amber
F.3.2	We will support carers to maintain their caring role through a personal outcome approach	Number of new carers supported	1,348 new carers have been supported in 2024-25 by Lanarkshire Carers. Lanarkshire Carers continues to experience high demand from new carers and carers already known to the organisation which currently totals 7,949 in South Lanarkshire which is a percentage demand increase of 22% in comparison with 2023-24. Lanarkshire Carers have continued to develop and evolve its “CarerSpace” online portal to start or continue a conversation. It is a toolkit developed by carers for carers that helps explore various aspects of a carers life, focusing on what matters to them. Once submitted, staff from Lanarkshire Carers can pick up the conversation with the carer.	Green